## Project Requirements
F2 FINTECH - FINANCIAL THERAPY AI PLATFORM
PROJECT VISION
Vision Statement: | Build an AI-powered Financial Therapy Platform that provides empathetic, human-like financial counseling and advisory services to F2 Fintech customers, helping them navigate their financial journey with emotional support and professional guidance.
Problem We Solve: | Customers taking loans often face financial stress, anxiety, and lack of guidance. They need more than just money - they need emotional support, financial education, and personalized advice throughout their loan journey.
Our Solution: | An AI chatbot trained to understand customer emotions, provide empathetic responses, offer financial therapy, educate about products, and act as a personal financial advisor - available 24/7.
Inspiration: | Healo (healo.infiheal.com) - Mental health therapy platform. We are adapting their model for financial wellness instead of mental health.
Target Users: | F2 Fintech customers: loan applicants, existing borrowers, people facing financial stress, customers needing financial planning guidance.
CORE FEATURES TO BUILD
Feature | Description | User Value | Priority | Timeline
Financial Therapy Chatbot | AI bot that understands emotions, provides empathy, discusses financial stress, anxiety, spending habits | Get emotional support during financial crisis | P0 | April-May
Financial Health Self-Test | Assessment quiz to evaluate financial wellness, stress levels, money management habits | Understand current financial health status | P0 | April
Personalized Advisory | AI provides tailored advice on loans, budgeting, savings, investments based on user profile | Get personalized financial guidance | P0 | May
Credit Decision Engine | Automated loan approval/rejection with ML-based risk assessment | Faster loan decisions | P0 | May
Financial Education | Bot educates about financial products, terms, loan process, credit scores | Learn financial concepts | P1 | May
Session History | Track all conversations, progress over time, financial goals achievement | Monitor personal growth | P1 | May
Progress Dashboard | Visual dashboard showing financial health score, goals, milestones | See progress visually | P1 | May
Crisis Detection | AI detects severe financial/emotional distress and escalates to human advisor | Get human help when needed | P2 | Future
TEAM STRUCTURE
Role | Name/Type | Primary Responsibilities | Key Deliverables
AI/DS Intern 1 | Gunjan Dhiman | Training data collection, data annotation, bot training, testing | Training datasets, conversation flows, test reports
AI/DS Intern 2 | Mohd. Adnan | Model selection, fine-tuning, prompt engineering, evaluation | Fine-tuned models, prompt templates, metrics
Backend Developer | Soumyadev | APIs, database, integration, deployment | Backend system, APIs, infrastructure
Product Manager | Aditya Rawal | Overall planning, coordination, requirements, review | Project plan, requirements doc, approvals

## Tech Stack & AI Models
TECHNICAL ARCHITECTURE & AI MODEL STRATEGY
TECHNOLOGY STACK
Layer | Technology | Purpose | Why This Choice | Owner | Status
Frontend | React.js + TypeScript | Web UI, Chatbot Interface | Industry standard, component-based, type-safe | Backend Dev | Planned
Frontend UI | Tailwind CSS + Shadcn/UI | Styling, Components | Modern, customizable, fast development | Backend Dev | Planned
Backend API | Python FastAPI | REST APIs, AI Integration | Fast, async, great for AI/ML integration | Backend Dev | Planned
Database | PostgreSQL | User data, sessions, history | Reliable, ACID compliant, good for analytics | Backend Dev | Planned
Vector DB | Pinecone / ChromaDB | Store embeddings, semantic search | Fast similarity search for RAG system | AI Interns | Planned
Cache | Redis | Session management, caching | Fast, reduces DB load | Backend Dev | Planned
AI - Primary LLM | Claude 3.5 Sonnet (Anthropic) | Main conversational AI | Best empathy, safety, long context | AI Interns | Selected
AI - Alternative | chat gpt 4.6 opex | Backup/comparison | Good performance, widely used | AI Interns | Planned
AI - Embeddings | OpenAI text-embedding-3-large | Convert text to vectors | High quality, good for semantic search | AI Interns | Selected
AI Framework | LangChain | LLM orchestration, chains, RAG | Simplifies AI workflows, production-ready | AI Interns | Selected
ML - Credit Scoring | Scikit-learn / XGBoost | Credit decision models | Proven for financial ML, interpretable | AI Interns | Planned
Deployment | Docker + AWS/Azure | Containerization, hosting | Scalable, industry standard | Backend Dev | Planned
Monitoring | Langfuse / LangSmith | LLM observability, tracing | Track AI performance, costs, issues | AI Interns | Planned
AI MODEL TRAINING STRATEGY
Approach | Description | Training Data Needed | Timeline | Who | Status
Prompt Engineering | Craft system prompts to make Claude/GPT act as empathetic financial therapist | Example conversations, therapy scripts, financial scenarios | Week 1-2 | AI Interns | In Progress
RAG (Retrieval Augmented Generation) | Build knowledge base of financial info, retrieve relevant context for responses | 1000+ financial docs, FAQs, loan guides, therapy techniques | Week 2-4 | AI Interns | Planned
Few-Shot Learning | Provide examples in prompts to guide bot behavior | 100+ example Q&A pairs showing desired responses | Week 1-3 | AI Interns | Planned
Fine-tuning (Optional) | Fine-tune base model on financial therapy conversations | 5000+ high-quality conversation pairs (if we go this route) | Week 6-8 | AI Interns | Maybe Later
Hybrid Approach (RECOMMENDED) | Use Claude API + RAG + Prompt Engineering (no fine-tuning needed) | Therapy scripts, financial knowledge base, conversation flows | Week 1-8 | AI Interns | Selected
Sentiment Analysis | Detect customer emotional state (stressed, anxious, happy) | Labeled emotional conversations (can use existing datasets) | Week 3-4 | AI Interns | Planned
Intent Classification | Classify user intent (seeking loan info, emotional support, complaint) | Labeled intents from conversations (500+ examples) | Week 2-3 | AI Interns | Planned
Our Approach | We train on: Financial scenarios, empathetic conversation patterns, financial education, loan guidance - NO mental health clinical data.
Empathy Source | Claude/GPT already have empathy built-in. We guide them with prompts to apply empathy to financial contexts.

## Learning Resources
LEARNING RESOURCES FOR TEAM
WEEK-BY-WEEK LEARNING PATH (AI/DS INTERNS)
Week | Topic | What to Learn | Resources | Outcome | Hours
Week 1 | LLM Fundamentals | What are LLMs, how they work, prompt engineering basics | OpenAI Prompt Engineering Guide, Anthropic Claude docs, YouTube: "LLM Basics" | Can write effective prompts | 12h
Week 1 | Understanding Healo | Analyze healo.infiheal.com - features, flow, UI/UX, therapy approach | Healo website, sign up for demo, document features | Feature comparison doc | 8h
Week 1-2 | Financial Therapy Concepts | Financial stress, anxiety, counseling techniques, empathetic communication | Books: "Financial Therapy", online courses on Coursera | Understand domain | 10h
Week 2 | LangChain Framework | Chains, agents, memory, RAG implementation | LangChain documentation, LangChain cookbook, YouTube tutorials | Build simple RAG demo | 16h
Week 2-3 | Vector Databases | Embeddings, similarity search, Pinecone/ChromaDB | Pinecone quickstart, Embedding guide (OpenAI) | Can store and search embeddings | 12h
Week 3 | Prompt Engineering Advanced | System prompts, few-shot, chain-of-thought, role-playing | Anthropic prompt library, OpenAI examples | Create therapy bot prompts | 12h
Week 3-4 | Data Collection & Annotation | How to gather training data, labeling, quality control | Data annotation best practices, Labelbox tutorials | Quality dataset created | 20h
Week 4 | Evaluation & Testing | How to evaluate LLM outputs, metrics, A/B testing | LangSmith docs, eval frameworks | Can test bot quality | 10h
Week 5 | Sentiment Analysis | Emotion detection, sentiment models | Hugging Face sentiment models, NLTK tutorials | Implement sentiment detection | 12h
Week 5-6 | Credit Scoring ML | Classification models, feature engineering, model evaluation | Scikit-learn docs, credit scoring papers | Understand credit models | 16h
Week 6-7 | Production Best Practices | Error handling, monitoring, logging, observability | LangFuse docs, production LLM guides | Production-ready code | 12h
Week 7-8 | Testing & Optimization | Load testing, cost optimization, latency reduction | Performance testing guides | Optimized system | 14h
ESSENTIAL RESOURCES LIBRARY
Category | Resource Name | Type | URL/Access | Priority | Notes
LLM Basics | Anthropic Claude Documentation | Docs | docs.anthropic.com | Critical | Our primary LLM
LLM Basics | OpenAI API Documentation | Docs | platform.openai.com/docs | High | Backup LLM
LLM Basics | Prompt Engineering Guide | Tutorial | promptingguide.ai | Critical | Learn prompting
RAG | LangChain Documentation | Docs | python.langchain.com | Critical | Framework we use
RAG | Pinecone Quickstart | Tutorial | docs.pinecone.io | High | Vector DB
Financial Domain | Financial Therapy Association | Website | financialtherapyassociation.org | Medium | Domain knowledge
Financial Domain | NFCC - Financial Counseling | Resources | nfcc.org | Medium | Counseling techniques
Data | Hugging Face Datasets | Platform | huggingface.co/datasets | High | Find existing datasets
ML | Scikit-learn Tutorials | Docs | scikit-learn.org | High | Credit scoring ML
Testing | LangSmith (LangChain) | Platform | smith.langchain.com | High | LLM observability
Testing | Langfuse | Platform | langfuse.com | Medium | Alternative monitoring
Dev Tools | GitHub Copilot | Tool | github.com/copilot | High | AI coding assistant
Community | r/LangChain Reddit | Forum | reddit.com/r/LangChain | Low | Community help
Community | LangChain Discord | Chat | Discord invite in docs | Low | Real-time help

## 60-Day AI Intern Roadmap
AI/DS INTERNS - 60 DAY DETAILED ROADMAP (Day-by-Day)
Day | Date | Phase | Tasks for the Day | Deliverable | Who | Status | Notes
Day 1 | 2026-04-01 | Onboarding | Project kickoff, team intro, setup accounts (GitHub, Anthropic, OpenAI) | Onboarding checklist completed | Both | Pending
Day 2 | 2026-04-02 | Understanding | Study Healo platform completely - create account, explore all features | Healo feature analysis doc | Intern 1 | Pending
Day 3 | 2026-04-03 | Understanding | Research financial therapy concepts, read articles on financial wellness | Financial therapy notes | Intern 2 | Pending
Day 4 | 2026-04-04 | Learning | Complete LLM basics tutorial, understand how Claude/GPT work | LLM fundamentals quiz passed | Both | Pending
Day 5 | 2026-04-05 | Learning | Prompt engineering basics - write first 10 prompts for financial bot | 10 sample prompts | Intern 1 | Pending
Day 6 | 2026-04-06 | Planning | Define user personas - who are our customers, what problems they face | User persona document | Intern 2 | Pending
Day 7 | 2026-04-07 | Planning | Create list of 50 financial stress scenarios customers might have | Scenario list (50 items) | Both | Pending
Day 8 | 2026-04-08 | Data Collection | Start collecting financial FAQ data from web, F2 Fintech docs | 100 FAQ pairs collected | Intern 1 | Pending
Day 9 | 2026-04-09 | Data Collection | Write conversation scripts for 10 common scenarios (loan anxiety, budgeting) | 10 conversation scripts | Intern 2 | Pending
Day 10 | 2026-04-10 | Learning | Learn LangChain basics, install and run hello world example | LangChain demo working | Both | Pending
Day 11 | 2026-04-11 | Data Collection | Design self-assessment questionnaire (20 questions for financial health) | Self-test question bank | Intern 1 | Pending
Day 12 | 2026-04-12 | Data Collection | Gather data on financial products (loans, credit cards) - create knowledge base | Product knowledge doc | Intern 2 | Pending
Day 13 | 2026-04-13 | Prompt Engineering | Create system prompt for empathetic financial therapist bot | System prompt v1 | Intern 1 | Pending
Day 14 | 2026-04-14 | Testing | Test system prompt with Claude API, refine based on outputs | Prompt test report | Intern 2 | Pending
Day 15 | 2026-04-15 | RAG Setup | Learn about embeddings, vector databases, semantic search | RAG concepts learned | Both | Pending
Day 16 | 2026-04-16 | RAG Setup | Setup Pinecone account, create first index, upload test data | Vector DB working | Intern 1 | Pending
Day 17 | 2026-04-17 | Data Collection | Collect 200 more Q&A pairs - focus on emotional scenarios | 200 Q&A pairs | Intern 2 | Pending
Day 18 | 2026-04-18 | Data Annotation | Label data with intents: loan_query, emotional_support, product_info, complaint | 100 labeled examples | Intern 1 | Pending
Day 19 | 2026-04-19 | Data Annotation | Label data with sentiment: stressed, anxious, happy, neutral, angry | 100 labeled examples | Intern 2 | Pending
Day 20 | 2026-04-20 | Development | Build simple RAG pipeline - upload knowledge base to vector DB | RAG demo v1 | Both | Pending
Day 21 | 2026-04-21 | Testing | Test RAG - ask questions, check if correct context is retrieved | RAG test results | Both | Pending
Day 22 | 2026-04-22 | Bot Development | Integrate Claude API with RAG pipeline | Bot v1 prototype | Intern 1 | Pending
Day 23 | 2026-04-23 | Bot Development | Add conversation memory - bot remembers previous messages | Memory feature working | Intern 2 | Pending
Day 24 | 2026-04-24 | Testing | Test bot with 20 sample conversations, collect feedback | Testing report | Both | Pending
Day 25 | 2026-04-25 | Improvement | Refine prompts based on testing, fix errors | Improved prompts v2 | Intern 1 | Pending
Day 26 | 2026-04-26 | Credit Engine | Research credit scoring - understand features like income, credit history, DTI | Credit scoring research doc | Intern 2 | Pending
Day 27 | 2026-04-27 | Credit Engine | Collect sample credit data (can use Kaggle datasets) | Credit dataset ready | Intern 1 | Pending
Day 28 | 2026-04-28 | Review | Week 4 review with PM - demo bot, discuss progress, plan May | Month 1 demo | Both | Pending
Day 29 | 2026-04-29 | ML Development | Build sentiment analysis model using existing libraries | Sentiment model working | Intern 1 | Pending
Day 30 | 2026-04-30 | ML Development | Build intent classification model | Intent classifier working | Intern 2 | Pending
Day 31 | 2026-05-01 | Integration | Integrate sentiment detection into bot - bot detects user emotions | Sentiment in bot | Intern 1 | Pending
Day 32 | 2026-05-02 | Integration | Integrate intent classification - bot understands what user wants | Intent in bot | Intern 2 | Pending
Day 33 | 2026-05-03 | Data Expansion | Expand training data to 500 total Q&A pairs | 500 Q&A dataset | Both | Pending
Day 34 | 2026-05-04 | Data Quality | Review and clean dataset - remove duplicates, fix errors | Clean dataset v2 | Intern 1 | Pending
Day 35 | 2026-05-05 | Testing | Test bot with expanded data, measure accuracy | Accuracy metrics | Intern 2 | Pending
Day 36 | 2026-05-06 | Bot Features | Add personalization - bot uses user name, remembers preferences | Personalization working | Intern 1 | Pending
Day 37 | 2026-05-07 | Bot Features | Add crisis detection - if user very stressed, suggest human advisor | Crisis detection module | Intern 2 | Pending
Day 38 | 2026-05-08 | Credit Model | Train ML model for credit scoring using scikit-learn | Credit model v1 | Intern 1 | Pending
Day 39 | 2026-05-09 | Credit Model | Evaluate model - accuracy, precision, recall, fairness check | Model evaluation report | Intern 2 | Pending
Day 40 | 2026-05-10 | Integration | Connect credit model to bot - bot can explain credit decisions | Integrated system | Both | Pending
Day 41 | 2026-05-11 | Knowledge Base | Expand knowledge base with more financial education content | Expanded KB (1000 docs) | Intern 1 | Pending
Day 42 | 2026-05-12 | Testing | End-to-end testing of all features together | E2E test results | Intern 2 | Pending
Day 43 | 2026-05-13 | Optimization | Optimize response time - cache common queries, faster embeddings | Performance improvements | Intern 1 | Pending
Day 44 | 2026-05-14 | Optimization | Reduce API costs - use cheaper models where appropriate | Cost optimization report | Intern 2 | Pending
Day 45 | 2026-05-15 | Quality | Implement guardrails - prevent harmful/incorrect financial advice | Safety guardrails | Intern 1 | Pending
Day 46 | 2026-05-16 | Quality | Add response validation - check for hallucinations, incorrect info | Validation system | Intern 2 | Pending
Day 47 | 2026-05-17 | Monitoring | Setup LangSmith for monitoring conversations, tracking metrics | Monitoring dashboard | Both | Pending
Day 48 | 2026-05-18 | Documentation | Write technical documentation - how bot works, architecture | Tech docs v1 | Intern 1 | Pending
Day 49 | 2026-05-19 | Testing | User testing with 5 beta testers, collect feedback | User feedback report | Intern 2 | Pending
Day 50 | 2026-05-20 | Bug Fixes | Fix all issues found in user testing | Bug fix list | Both | Pending
Day 51 | 2026-05-21 | UI Integration | Work with backend dev to integrate bot into frontend | Frontend integration | Both | Pending
Day 52 | 2026-05-22 | Final Testing | Comprehensive testing - all scenarios, edge cases | Final test report | Both | Pending
Day 53 | 2026-05-23 | Training Data | Final dataset review - ensure 1000+ high quality pairs | Final dataset v3 | Intern 1 | Pending
Day 54 | 2026-05-24 | Documentation | Complete user guide - how to use the platform | User guide | Intern 2 | Pending
Day 55 | 2026-05-25 | Demo Prep | Prepare final demo for stakeholders | Demo script & slides | Both | Pending
Day 56 | 2026-05-26 | Launch Prep | Final checklist, deployment readiness check | Launch checklist | Both | Pending
Day 57 | 2026-05-27 | Launch | Soft launch with limited users, monitor closely | Launch report | Both | Pending
Day 58 | 2026-05-28 | Monitoring | Monitor first day usage, fix any critical issues | Day 1 monitoring | Both | Pending
Day 59 | 2026-05-29 | Analysis | Analyze usage data, conversation quality, user satisfaction | Analytics report | Both | Pending
Day 60 | 2026-05-30 | Handoff | Knowledge transfer to backend team, future roadmap planning | Handoff document | Both | Pending

## April Tasks by Week
APRIL 2026 - WEEKLY TASK BREAKDOWN
Week | Task | Description | Owner | Priority | Hours | Deliverable | Dependencies | Status
Week 1 | Healo Platform Deep Dive | Complete analysis of Healo - features, user flow, tech analysis | AI Intern 1 | P0 | 16 | Healo Analysis Doc | - | Not Started
Week 1 | Competitor Research | Research financial wellness platforms (Finfit, Wysa, others) | AI Intern 2 | P1 | 12 | Competitor Comparison | - | Not Started
Week 1 | LLM Fundamentals Learning | Learn how Claude/GPT work, API usage, prompt basics | Both Interns | P0 | 16 | LLM Knowledge | - | Not Started
Week 1 | User Persona Definition | Create detailed personas for loan customers | PM + Interns | P0 | 8 | Persona Document | - | Not Started
Week 1 | Project Setup | GitHub repo, docs structure, team communication setup | Backend Dev | P0 | 8 | Repo Ready | - | Not Started
Week 2 | Financial Scenarios List | Document 50+ scenarios of customer financial stress | AI Intern 1 | P0 | 16 | 50 Scenarios | Week 1 Personas | Not Started
Week 2 | Therapy Script Writing | Write 10 example therapy conversations for financial counseling | AI Intern 2 | P0 | 20 | 10 Therapy Scripts | Scenarios | Not Started
Week 2 | Self-Test Design | Create 20-question financial health assessment | AI Intern 1 | P0 | 16 | Question Bank | Scenarios | Not Started
Week 2 | LangChain Learning | Learn RAG, chains, agents, memory management | Both Interns | P0 | 20 | LangChain Skills | - | Not Started
Week 2 | System Architecture | Design overall system - APIs, DB, AI components | Backend Dev | P0 | 20 | Architecture Diagram | - | Not Started
Week 3 | Training Data Collection | Collect 500 Q&A pairs for bot training | AI Intern 2 | P0 | 30 | 500 Q&A Dataset | Scripts | Not Started
Week 3 | Data Annotation | Label data with intents and sentiments | AI Intern 1 | P0 | 20 | Labeled Dataset | Q&A Data | Not Started
Week 3 | Vector DB Setup | Setup Pinecone/ChromaDB, create embeddings | AI Intern 2 | P0 | 16 | Vector DB Working | Training Data | Not Started
Week 3 | System Prompt Creation | Craft empathetic financial therapist system prompt | AI Intern 1 | P0 | 12 | System Prompt v1 | Scripts | Not Started
Week 3 | API Design | Design REST APIs for chat, assessment, user management | Backend Dev | P0 | 16 | API Specification | Architecture | Not Started
Week 4 | Bot Prototype v1 | Build working bot with Claude API + RAG | Both Interns | P0 | 32 | Working Bot Prototype | All Week 3 | Not Started
Week 4 | Bot Testing | Test with 20 conversations, collect feedback | Both Interns | P0 | 16 | Test Results | Bot Prototype | Not Started
Week 4 | Self-Test Backend | Build API for self-assessment scoring | Backend Dev | P0 | 20 | Assessment API | API Design | Not Started
Week 4 | Self-Test Frontend | Basic UI for financial health test | Backend Dev | P1 | 16 | Test UI | Assessment API | Not Started
Week 4 | Credit Engine Planning | Document credit engine requirements | PM + Interns | P0 | 12 | Credit Requirements | - | Not Started
Week 4 | Month Review | Review progress, demo to stakeholders, plan May | All Team | P0 | 8 | Demo & Report | Bot Prototype | Not Started

## May Tasks by Week
MAY 2026 - WEEKLY TASK BREAKDOWN
Week | Task | Description | Owner | Priority | Hours | Deliverable | Dependencies | Status
Week 1 | Sentiment Analysis Model | Build emotion detection for user messages | AI Intern 1 | P0 | 24 | Sentiment Model | April Bot | Not Started
Week 1 | Intent Classification | Build intent detector (loan query, support, complaint) | AI Intern 2 | P0 | 24 | Intent Classifier | April Bot | Not Started
Week 1 | Data Expansion | Expand dataset to 1000 Q&A pairs | Both Interns | P0 | 32 | 1000 Q&A Dataset | April 500 | Not Started
Week 1 | Conversation Memory | Implement context tracking across messages | AI Intern 1 | P0 | 16 | Memory System | Bot v1 | Not Started
Week 2 | Bot v2 Integration | Integrate sentiment + intent + memory into bot | Both Interns | P0 | 32 | Bot v2 Complete | Week 1 May | Not Started
Week 2 | Personalization | Add user name, preferences, history to responses | AI Intern 1 | P1 | 16 | Personalized Bot | Bot v2 | Not Started
Week 2 | Crisis Detection | Detect severe stress, suggest human advisor | AI Intern 2 | P1 | 16 | Crisis Module | Sentiment Model | Not Started
Week 2 | Chat UI Development | Build production chat interface | Backend Dev | P0 | 32 | Chat Interface | Bot v2 | Not Started
Week 2 | Dashboard Design | Create user dashboard with health score | Backend Dev | P1 | 24 | Dashboard UI | - | Not Started
Week 3 | Credit Scoring Model | Build ML model for loan approval | AI Intern 1 | P0 | 32 | Credit ML Model | April Planning | Not Started
Week 3 | Credit Model Evaluation | Test accuracy, fairness, bias check | AI Intern 2 | P0 | 16 | Eval Report | Credit Model | Not Started
Week 3 | Credit API Development | Build API for credit decisions | Backend Dev | P0 | 24 | Credit API | Credit Model | Not Started
Week 3 | Bot-Credit Integration | Connect bot with credit engine | Both Interns + Dev | P0 | 24 | Integrated System | Both Systems | Not Started
Week 3 | Knowledge Base Expansion | Add 1000+ financial education docs | AI Intern 2 | P1 | 20 | Expanded KB | - | Not Started
Week 4 | Performance Optimization | Reduce latency, optimize costs | AI Intern 1 | P0 | 20 | Performance Report | Full System | Not Started
Week 4 | Security Implementation | Add auth, encryption, data privacy | Backend Dev | P0 | 24 | Security Layer | - | Not Started
Week 4 | Guardrails & Validation | Prevent harmful advice, check accuracy | AI Intern 2 | P0 | 16 | Safety System | Bot v2 | Not Started
Week 4 | End-to-End Testing | Comprehensive testing of all features | All Team | P0 | 32 | Test Report | All Features | Not Started
Week 4 | Monitoring Setup | LangSmith/Langfuse for observability | Both Interns | P0 | 16 | Monitoring Dashboard | - | Not Started
Week 4 | Documentation | Technical docs, user guide, API docs | All Team | P0 | 24 | Complete Docs | - | Not Started
Week 4 | Beta Launch Prep | Final testing, beta user recruitment | PM + Team | P0 | 16 | Beta Ready | All Tasks | Not Started
Week 4 | Final Demo | Stakeholder demo, feedback collection | All Team | P0 | 8 | Demo Complete | Beta Ready | Not Started

## Total Deliverables
COMPLETE DELIVERABLES SUMMARY (60 DAYS)
Category | Deliverable | Description | Owner | Status | Quality Metrics
Data | Training Dataset | 1000+ high-quality Q&A pairs for bot training | AI Interns | In Progress | Quality score >90%, diverse scenarios
Data | Labeled Dataset | Data labeled with intents & sentiments | AI Interns | Planned | >95% inter-annotator agreement
Data | Financial Scenarios | 50+ documented customer stress scenarios | AI Interns | Planned | Covers all major use cases
Data | Knowledge Base | 1000+ documents on financial products & education | AI Interns | Planned | Accurate, up-to-date, F2 specific
Data | Self-Test Questions | 20-question financial health assessment | AI Intern 1 | Planned | Validated by financial expert
Data | Credit Training Data | Dataset for credit scoring model | AI Interns | Planned | Representative, unbiased
AI Models | Financial Therapy Bot | Empathetic AI chatbot using Claude/GPT + RAG | AI Interns | In Progress | >85% user satisfaction, <2s response
AI Models | Sentiment Analysis | Emotion detection from user messages | AI Intern 1 | Planned | >80% accuracy on test set
AI Models | Intent Classifier | Classify user intent from message | AI Intern 2 | Planned | >85% accuracy
AI Models | Credit Scoring Model | ML model for loan approval decisions | AI Intern 1 | Planned | >75% accuracy, fair across demographics
AI Models | RAG Pipeline | Retrieval system for knowledge base | AI Interns | Planned | <1s retrieval, >90% relevance
Backend | Chat API | REST API for chatbot interactions | Backend Dev | Planned | <200ms latency, 99% uptime
Backend | Assessment API | API for self-test scoring | Backend Dev | Planned | Accurate scoring, fast
Backend | Credit API | API for credit decisions | Backend Dev | Planned | Secure, auditable, compliant
Backend | User Management | Auth, profiles, sessions | Backend Dev | Planned | Secure, GDPR compliant
Backend | Database Schema | PostgreSQL schema for all data | Backend Dev | Planned | Normalized, scalable
Backend | Vector Database | Pinecone/ChromaDB for embeddings | AI Interns | Planned | Fast, scalable
Frontend | Chat Interface | Modern chat UI for conversations | Backend Dev | Planned | Intuitive, responsive, accessible
Frontend | Self-Test UI | Interface for financial health test | Backend Dev | Planned | Clear, engaging, mobile-friendly
Frontend | User Dashboard | Dashboard showing health score, progress | Backend Dev | Planned | Visual, insightful, real-time
Documentation | Technical Docs | System architecture, API docs, code docs | All Team | Planned | Complete, clear, up-to-date
Documentation | User Guide | How to use the platform | AI Interns | Planned | Easy to understand for non-tech users
Documentation | Training Manual | How to improve/maintain the bot | AI Interns | Planned | Enables future improvements
Documentation | API Documentation | REST API reference | Backend Dev | Planned | Complete with examples
Quality | Testing Suite | Unit, integration, E2E tests | All Team | Planned | >80% code coverage
Quality | Monitoring Dashboard | LangSmith/Langfuse observability | AI Interns | Planned | Real-time metrics, alerts
Quality | Guardrails System | Prevent harmful/incorrect advice | AI Intern 2 | Planned | Catches >95% of policy violations
Quality | Security Audit | Security implementation & testing | Backend Dev | Planned | No critical vulnerabilities
PROJECT STATISTICS
Total Deliverables: | 28 | Data: 6, AI Models: 5, Backend: 7, Frontend: 3, Docs: 4, Quality: 4
Total Team Members: | 4 | 2 AI/DS Interns + 1 Backend Developer + 1 PM
Timeline: | 60 days | April 1 - May 31, 2026
Total Estimated Hours: | ~1,200 hours | Across all team members
Key Technologies: | 10+ | Claude API, LangChain, FastAPI, React, PostgreSQL, Pinecone, etc.